## Sheet1
S.No | Assumption and reason | If incorrect
1 | Clinician-approved emergency escalation protocols exist because AI must not independently diagnose patients. | Develop and approve protocols before clinical workflows go live.
2 | Portal users can be authenticated, while phone and SMS require additional verification for sensitive actions. | Introduce an approved identity-verification service or restrict sensitive workflows.
3 | Healthcare vendors handling patient information will have appropriate contractual safeguards, including BAAs where required. | Exclude unsuitable vendors and disable affected processing paths.
4 | Epic supports approved interfaces for selected patient and scheduling operations. | Replace unavailable integrations with staff-managed tasks.
5 | Scheduling policies and provider availability can be obtained for the pilot clinic. | Launch appointment-request intake instead of autonomous booking.
6 | Medication refills require authorized clinical review. | Implement only workflows explicitly approved by the clinical leadership.
7 | Insurance and authorization data may be incomplete or delayed. | Avoid definitive coverage claims and route uncertain cases to trained staff.
8 | Saguaro can provide a reliable hospital-discharge worklist or notification feed. | Use a controlled staff-uploaded worklist until integration is available.
9 | English and Spanish support are required, with human escalation for low-confidence conversations. | Restrict automation to languages that meet validated quality standards.
10 | One pilot clinic can provide staff ownership, escalation coverage, and operational feedback. | Reduce the scope or delay launch until safe fallback support is available.